## Ark1
SWC,SWD,ITO
Covid-19 test- center | [6 empty] | Project Start: 03/05/2021 | [8 empty] | Project End: 02/06/2021 | [8 empty] | Customer: Sundhedsstyrelsen
By: "4 People" group
[5 empty] | May 03, 2021 | [6 empty] | May 10, 2021 | [6 empty] | May 17, 2021 | [6 empty] | May 24, 2021 | [6 empty] | May 31, 2021
[5 empty] | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
Tasks |  | Progress | Start | End | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Iception
Group Contract |  | 100% | 2021-05-13 | 2021-05-14 | bar: May 10, 2021 13
Phase Plan |  | 100% | 2021-05-12 | 2021-05-14 | bar: May 10, 2021 12 to May 10, 2021 14
Feasibility Study |  | 100% | 2021-05-12 | 2021-05-13 | bar: May 10, 2021 12 to May 10, 2021 13
Risk analysis |  | 100% | 2021-05-12 | 2021-05-13 | bar: May 10, 2021 12 to May 10, 2021 13
SWOT analysis |  | 100% | 2021-05-12 | 2021-05-13 | bar: May 10, 2021 12 to May 10, 2021 13
Stakeholder analysis |  | 100% | 2021-05-12 | 2021-05-13 | bar: May 10, 2021 12 to May 10, 2021 13
Use Case diagram |  | 100% | 2021-05-12 | 2021-05-12 | bar: May 10, 2021 12
List of requirements |  | 100%
Problem statement |  | 100%
Problem analyzes |  | 100%
Project limitation |  | 100%
Elaboration
Interation 1
Domain Model |  | 0%
Glossary |  | 0%
ER- diagram |  | 0%
Class Diagram |  | 100%
Use Case description |  | 0%
Data Base |  | 0%
Extra Specifications | FURPS
UML
Activity Diagram
System Sequence Diagram
Sequence Diagram
State Diagrams
Package Diagram
Information Expert
Creator
Low Coupling
High Cohesion
Controller
Polymorphism
Pure Fabrication
Indirection
Quality of design
Quality of conformance
Unit testing
Integration testing
Debugging
Normalization of tables
Construction
Code & Test
Transition
Hand In |  | 0% | bar: May 31, 2021 2